## Agile Product Backlog
PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
T1 | Theme: Product CRUD | Sprint 1 | Developer, QA and Scrum Master | 2019-09-04 | 2019-09-08 | Yes | Yes | High | Complete | 10 | Yes
T1U1 | As an admin,I want to add product details So that It will be available. 3 WD | Research on Burn down chart, CICD using Jenkins, create product backlog | Romisha Thapa (Scrum Master) | 2019-09-04 | 2019-09-04 | Yes | Yes | High | Complete | 2 | Yes
T1U2 | U5: As a customer, I want to view the available cakes so that I can obtain the information on cakes. 3 WD | Prepare sprint backlog, learn, practice and implement TTD for product CRUD, research CICD using Jenkins | Sushan Shrestha(QA) | 2019-09-04 | 2019-09-05 | Yes | Yes | High | Complete | 3 | Yes
T1U3 | As a customer, I want to view ordered products so that I can view my pending orders. 2 WD | Prepare sprint backlog, learn, practice and implement TTD for product CRUD, research CICD using Jenkins | Netra Dahal (QA) | 2019-09-05 | 2019-09-06 | Yes | Yes | High | Complete | 3 | Yes
T1U4 | U12: As an admin, I want to update cake details so that I can correct or edit existing cake information. 2 WD | Prepare and execute test plan, implement product CRUD in django | Biju Ale(Developer) | 2019-09-06 | 2019-09-08 | Yes | Yes | High | Complete | 2 | Yes
T2 | Theme: User Authentication | Sprint 2 | Developer, QA and Scrum Master | 2019-09-09 | 2019-09-16 | Yes | Yes | High | Complete |  | Yes
T2U1 | As a user I want to register account so that I can create profile. 3 WD | Create test case. Create registration logic, apply validation | Romisha Thapa (Scrum Master) | 2019-09-09 | 2019-09-11 | Yes | Yes | High | Complete | 17 | Yes
T2U2 | As a user, I want to login so that I can authenticate. 2 WD | Create test case. Create user login authentication system with regards to validation checks. Verify proper page redirection. | Sushan Shrestha(QA) | 2019-09-10 | 2019-09-12 | Yes | Yes | High | Complete | 12 | Yes
T2U3 | As a user, I want to logout the account so that I can clear my state. 1 WD | Create test case. Create a logout interface. Verify page redirection for accounts is working if session is cleared. | Netra Dahal (QA) | 2019-09-11 | 2019-09-13 | Yes | Yes | High | Complete | 7 | Yes
T2U4 | As a user, i want to edit profile so that I can correct the details. 2 WD | Create test case. Field validation is checked with profile updation | Biju Ale(Developer) | 2019-09-12 | 2019-09-16 | Yes | Yes | High | Complete | 9 | Yes
T3 | Theme: Product searching, select and add to cart | Sprint 3 | Developer, QA and Scrum Master | 2019-09-16 | 2019-09-23 | Yes | Yes | High | Complete | 9 | Yes
T3U1 | As a customer, I want to select product quantities so that I can order the multiple products at one time. 1 WD | Create test case. Create product qty increment/decrement interface. Make sure it updates in the cart summary with price total consideration. | Romisha Thapa (Scrum Master) | 2019-09-16 | 2019-09-18 | Yes | Yes | High | Complete | 18 | Yes
T3U2 | As a customer, I want to add the product to the cart so that I can buy the product. 3 WD | Create a test case. Create a cart model. Check if correct items are displayed in the summary. | Sushan Shrestha(QA) | 2019-09-18 | 2019-09-20 | Yes | Yes | High | Complete | 13 | Yes
T3U3 | As a customer, I want to search for specific cakes so that I can find what I want. 2 WD | Create a test case. Create a serach API that returns results in various parameters. | Netra Dahal (QA) | 2019-09-18 | 2019-09-23 | Yes | Yes | High | Complete |  | Yes
T4 | Theme: Product check-out and cancellation | Sprint 4 | Developer, QA and Scrum Master | 2019-09-23 | 2019-09-30 | Yes | Yes | High | Complete |  | Yes
T4U1 | As a customer, I want to check-out the cart items so that I can confirm the order. 8 WD | Create a test case. Car-chec out functionality must be integrated that sends the order summary to the admin dashboard. | Romisha Thapa (Scrum Master) | 2019-09-23 | 2019-09-25 | Yes | Yes
T4U2 | As a customer, I want to cancel the order so that I can eliminate the unwanted orders. 1 WD | Create a test case. Admin dashboard must provide the interface to purge respective orders of a customer. | Sushan Shrestha(QA) | 2019-09-25 | 2019-09-30 | Yes | Yes
T5 | Theme: View and Manage Ordered product | Sprint 5 | Developer, QA and Scrum Master | 2019-09-30 | 2019-10-07 | Yes | Yes | High | Complete |  | Yes
T5U1 | As an admin, I want to view the ordered products so that I can proceed. 5 WD | Create test case. Order summary must be displayed in admin dashboard for each customers. | Romisha Thapa (Scrum Master) | 2019-09-30 | 2019-10-02 | Yes | Yes | High | Complete | 18 | Yes
T5U2 | As an admin, I want to mark the status of customer order so that I can process the order. 1 WD | Create test case. Admin dashboard must provide marker to mark the order has complete. | Sushan Shrestha(QA) | 2019-10-02 | 2019-10-05 | Yes | Yes | High | Complete | 20 | Yes
T5U3 | As an admin, I want to suspend the cake entry so that I can remove the deprecated cake. 1 WD | Create test case. Admin dashboard must provide interface to delete cake entries | Netra Dahal (QA) | 2019-10-05 | 2019-10-07 | Yes | Yes | High | Complete | 25 | Yes
T6 | Theme: History | Sprint 6 | Developer, QA and Scrum Master | 2019-10-07 | 2019-10-14 | Yes | Yes | High | Complete |  | Yes
T6U1 | As an admin, I want to view order history so that I can track past transactions. 2 WD | Create test case. View status of past orders for each customers. | Romisha Thapa (Scrum Master) | 2019-10-07 | 2019-10-10 | Yes | Yes | High | Complete |  | Yes
T6U2 | As a custom, I want to view order history so that I can track past history. 2 WD | Create test case. Create an interface to view past tranasactions. | Sushan Shrestha(QA) | 2019-10-10 | 2019-10-14 | Yes | Yes | High | Complete | 20 | Yes
T7 | Theme: Push Notification and Communication | Sprint 7 | Developer, QA and Scrum Master | 2019-10-14 | 2019-10-21 | Yes | Yes | High | Complete |  | Yes
T7U1 | As an admin, I want to state the ETA (Estimated Time of Arrival) so that I can notify the customer. 3 WD | Create test case. Optional feature. Order summary must be correctly sent to the admin dashboard. | Romisha Thapa (Scrum Master) | 2019-10-14 | 2019-10-18 | Yes | Yes | High | Complete |  | Yes
T7U2 | As an admin, I want to view customer details so that I can contact the customer later. 2WD | Create test case. Make sure order summary has customer address bound to each customer. | Sushan Shrestha(QA) | 2019-10-18 | 2019-10-21 | Yes | Yes | High | Complete |  | Yes

## Dropdown options
This section is for the drop-down list
Yes | High | Complete
No | Medium | In Progress
| Low | Not started
|  |  | wd | sprint
|  |  | 6 | 1
|  |  | 1 | 0.16667

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.