## Agile Project Plan
PROJECT PLAN
PROJECT NAME | Scrum Master | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
Cake WebApp | Romisha Thapa | 2019-09-04 | 2019-10-21 |  | 100% | SCOPE STATEMENT
TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | STATUS
Sprint 1 | Security | Biju Ale | 40 | 2019-09-04 | 2019-09-08 | Complete
Feature 1 | User Registration | Sushan Tha Shrestha |  | 2019-09-05 | 2019-09-06 | Complete
Feature 2 | Login | Romisha Thapa |  | 2019-09-06 | 2019-09-07 | Complete
Feature 3 | Logout | Netra Dahal |  | 2019-09-07 | 2019-09-08 | Complete
Sprint 2 | Compliance | Biju Ale | 40 | 2019-09-09 | 2019-09-16 | Complete
Feature 4 | Product addition | Sushan Tha Shrestha |  | 2019-09-10 | 2019-09-12 | Complete
Feature 5 | Profile edition | Romisha Thapa |  | 2019-09-12 | 2019-09-14 | Complete
Feature 6 | Search product | Netra Dahal |  | 2019-09-14 | 2019-09-16 | Complete
Sprint 3 | Compliance | Biju Ale | 40 | 2019-09-13 | 2019-09-23 | Complete
Feature 7 | Product Qty selection | Sushan Tha Shrestha |  | 2019-09-13 | 2019-09-17 | Complete
Feature 8 | Cart checkout | Netra Dahal |  | 2019-09-17 | 2019-09-23 | Complete
Sprint 4 | Compliance | Netra Dahal | 40 | 2019-09-23 | 2019-09-30 | Complete
Feature 7 | Order cancellation | Sushan Tha Shrestha |  | 2019-09-23 | 2019-09-25 | Complete
Feature 8 | Order history view | Biju Ale |  | 2019-09-25 | 2019-09-30 | Complete
Sprint 5 | Usability | Biju Ale | 40 | 2019-09-30 | 2019-10-07 | Complete
Feature 7 | Product order view | Romisha Thapa |  | 2019-09-30 | 2019-10-03 | Complete
Feature 8 | Customer order mark | Netra Dahal |  | 2019-10-03 | 2019-10-05 | Complete
Feature 9 | Suspend cake entry | Romisha Thapa |  | 2019-10-05 | 2019-10-07 | Complete
Sprint 6 |  | Biju Ale | 40 | 2019-10-07 | 2019-10-14 | Complete
Feature 7 | Improve the order history views. | Netra Dahal |  | 2019-10-07 | 2019-10-11 | Complete
Feature 8 | track past history | Sushan Tha Shrestha |  | 2019-10-11 | 2019-10-14 | Complete
Sprint 7 |  | Biju Ale | 40 | 2019-10-14 | 2019-10-21 | Complete
Feature 7 | Estimate time arrival | Sushan Tha Shrestha |  | 2019-10-14 | 2019-10-17 | Complete
Feature 8 | view customer details | Romisha Thapa |  | 2019-10-17 | 2019-10-21 | Complete

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.