## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
T2U1: As a user I want to register account so that I can create profile | 17 | All | DIONE | 17 | 5 | 5 | 4 | 2 | 1 |  | 17
Create regiration test case | 4 | Sushan Tha Shrestha | DONE | 4 | 2 | 1 | 1 | 1 | 0 |  | 5
Create user model | 4 | Netra Dahal | DONE | 4 | 1 | 1 | 1 | 1 | 0 |  | 4
Create routes and view | 6 | Biju Ale | DONE | 6 | 1 | 1 | 1 | 0 | 0 |  | 3
Review and push | 3 | Romisha Thapa | DONE | 3 | 1 | 2 | 1 | 0 | 1 |  | 5
T2U2: As a user, I want to login so that I can authenticate. | 12 | All | DONE | 12 | 4 | 2 | 2 | 2 | 2 |  | 12
Create login test case | 4 | Netra Dahal | DONE | 4 | 1 | 0.5 | 0.5 | 0 | 0.5 |  | 2.5
Create password vertiication module | 3 | Sushan Tha Shrestha | DONE | 3 | 1 | 0.5 | 0.5 | 0.5 | 0.5 |  | 3
Create routes and views | 3 | Biju Ale | DONE | 3 | 1 | 1 | 0.5 | 1.5 | 0 |  | 4
Review and push | 2 | Romisha Thapa | DONE | 2 | 1 | 0 | 0.5 | 0 | 1 |  | 2.5
T2U3: As a user, I want to logout the account so that I can clear my state. | 7 | All | DONE | 7 | 3 | 2 | 1.5 | 0.5 | 0 | 0 | 7
Create test case for logout | 3 | Biju Ale | DONE | 3 | 1 | 1.5 | 0.5 |  |  |  | 3
Create routes and views | 2 | Netra Dahal | DONE | 2 | 1 |  | 0.5 |  | 0 |  | 1.5
Review and push | 2 | Romisha Thapa | DONE | 2 | 1 | 0.5 | 0.5 | 0.5 | 0 |  | 2.5
TOTAL |  |  |  | 72 | 19 | 18 | 15 | 9 | 6 |  | 72

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.