## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
T3U2: As a customer, I want to add the product to the cart so that I can buy the product | 13 | All | DONE | 13 | 4 | 3 | 2.5 | 2 | 1.5 | 0 | 13
Create cart model | 4 | Biju Ale | DONE | 4 | 1 | 0.5 | 0 | 0 | 0 | 0 | 1.5
Create test case to add to cart | 4 | Sushan Tha Shrestha | DONE | 4 | 1 | 0.5 | 0.5 | 1 |  | 0 | 3
Create routes and view | 2 | Netra Dahal | DONE | 2 | 1 | 1 | 1 | 0.75 | 0.5 |  | 4.25
Review and push | 3 | Romisha Thapa | DONE | 3 | 1 | 1 | 1 | 0.25 | 1 |  | 4.25
T2U4: As a user, i want to edit profile so that I can correct the details. | 9 | All | DONE | 9 | 3 | 2.5 | 1 | 1 | 1 | 0.5 | 9
Create update test case. | 4 | Sushan Tha Shrestha | DONE | 4 | 1 | 1 |  | 1 |  | 0.5 | 3.5
Create routes and views | 3 | Netra Dahal | DONE | 3 | 1 | 0.5 | 1 |  | 1 |  | 3.5
Review and push | 2 | Romisha Thapa | DONE | 2 | 1 | 1 |  |  |  |  | 2
T3U3 As a customer, I want to search for specific cakes so that I can find what I want | 9 | All | DONE | 9 | 3 | 2 | 1 | 1.5 | 0.5 | 1 | 9
create search test case | 4 | Netra Dahal | DONE | 4 | 1 | 1 | 0.5 |  | 0.5 |  | 3
developed search system in application | 3 | Biju Ale | DONE | 3 | 1 | 0.75 | 0.5 | 1 | 0 |  | 3.25
Review and push | 2 | Romisha Thapa | DONE | 2 | 1 | 0.25 | 0 | 0.5 | 0 | 1 | 2.75
TOTAL |  |  |  | 44 | 14 | 11 | 7 | 6 | 5 |  | 44

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.