## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
T3U1 As a customer, I want to select product quantities so that I can order the multiple products at one time. | 18 | All |  | 18 | 4.5 | 4 | 3.5 | 3 | 2 | 1 | 18
Create select multiple ordered products test case | 6 | Sushan Tha Shrestha | DONE | 6 | 1 | 1.5 | 1 | 0 | 1 | 0 | 6
Implement select multiple ordered products | 6 | Netra Dahal | DONE | 6 | 1.5 | 1 | 1 | 0.5 |  | 0.5 | 6
create multiple product quantities | 4 | Biju Ale | DONE | 4 | 1 | 1 | 1 | 2.5 | 1 | 0 | 4
Review and push | 2 | Romisha Thapa | DONE | 2 | 1 | 0.5 | 0.5 | 0 | 0 | 0.5 | 2
T4U1 As a customer, I want to check-out the cart items so that I can confirm the order | 20 | All | DONE | 20 | 6 | 5.5 | 3 | 2 | 2 | 1.5 | 20
Create test case of item checkout | 7 | Netra Dahal | DONE | 7 | 2 | 2 |  | 1 | 1 |  | 7
Implement | 7 | Biju Ale | DONE | 7 | 1 | 2 | 1 | 1 | 1 | 0.5 | 7
Create routes and views | 3 | Sushan Tha Shrestha | DONE | 3 | 2 | 1.5 | 1 | 0 | 0 |  | 3
Review and push | 3 | Romisha Thapa | DONE | 3 | 1 | 0 | 1 |  | 0 | 1 | 3
TOTAL |  |  |  | 76 | 16.5 | 19 | 13 | 10 | 8 |  | 76

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.