## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
T4U2 As a customer, I want to cancel the order so that I can eliminate the unwanted orders. | 18 | All | DONE | 18 | 4.5 | 4 | 3.5 | 3 | 2 | 1 | 18
create a test case for cancle order | 6 | Sushan Tha Shrestha | DONE | 6 | 1 | 1 | 1 | 1 | 0 | 0 | 4
create a test case of list of unwanted orders | 6 | Netra Dahal | DONE | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 4.5
Implement cancel order | 4 | Biju Ale | DONE | 4 | 1 | 1 | 1 | 1 | 1 | 0.5 | 5.5
Review and push | 2 | Romisha Thapa | DONE | 2 | 1.5 | 1 | 0.5 | 0 | 0.5 | 0.5 | 4
T6U2 As a custom, I want to view order history so that I can track past history. | 20 | All | DONE | 20 | 5 | 4.5 | 4 | 3.5 | 2 | 1 | 20
Create test case of order history | 7 | Netra Dahal | DONE | 7 | 2 | 1 | 1 | 0.5 | 0.25 | 0 | 7
Implement | 7 | Biju Ale | DONE | 7 | 1 | 2 | 1 | 2 | 1 | 1 | 7
Create routes and views | 3 | Sushan Tha Shrestha | DONE | 3 | 1 | 1 | 1 | 1 |  | 0 | 3
Review and push | 3 | Romisha Thapa | DONE | 3 | 1 | 0.5 | 1 | 0 | 0.75 | 0 | 3
TOTAL |  |  |  | 76 | 14.5 | 17 | 15 | 13 | 8 |  | 76

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.