## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
T5U1 As an admin, I want to view the ordered products so that I can proceed. | 18 | All | DONE | 18 | 6.5 | 5.5 | 2 | 2 | 1.5 | 0.5 | 18
Create view ordered products test case | 6 | Sushan Tha Shrestha | DONE | 5 | 2 | 1.5 | 0 | 0.5 | 1 |  | 5
Implement view ordered products | 6 | Netra Dahal | DONE | 5 | 2 | 1.5 | 1 | 0.5 | 0 |  | 5
create routes and views | 4 | Biju Ale | DONE | 6 | 1 | 2 | 1 | 1 | 0.5 | 0.5 | 6
Review and push | 2 | Romisha Thapa | DONE | 2 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 2
T5U2 As an admin, I want to mark the status of customer order so that I can process the order. | 20 | All | DONE | 20 | 5 | 4.5 | 4 | 2.5 | 2 | 2 | 20
Create test case to mark the status of the customer | 7 | Netra Dahal | DONE | 6 | 2 | 1 | 1 | 1 | 1 |  | 6
Implement | 7 | Biju Ale | DONE | 7 | 1 | 2 | 1 | 1 | 1 | 1 | 7
Create routes and views | 3 | Sushan Tha Shrestha | DONE | 3 | 1 | 1 | 1 | 0 | 0 |  | 3
Review and push | 3 | Romisha Thapa | DONE | 4 | 1 | 0.5 | 1 | 0.5 | 0 | 1 | 4
T5U3 As an admin, I want to suspend the cake entry so that I can remove the deprecated cake. | 25 | All | DONE | 25 | 5.5 | 5 | 4.5 | 4 | 3 | 3 | 25
Create test case to suspend the cake entry | 7 | Sushan Tha Shrestha | DONE | 7 | 1 | 2 | 1 | 1 | 1 | 1 | 7
Implement | 8 | Netra Dahal | DONE | 7 | 2 | 1 | 1 | 1 | 1 | 1 | 7
Create routes and views | 7 | Biju Ale | DONE | 8 | 2 | 1 | 2 | 1 | 1 | 1 | 8
Review and push | 3 | Romisha Thapa | DONE | 3 | 0.5 | 1 | 0.5 | 1 | 0 |  | 3
TOTAL |  |  |  | 126 | 27.5 | 30 | 21 | 17 | 13 |  | 126

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.