## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
T7U1 As an admin, I want to state the ETA (Estimated Time of Arrival) so that I can notify the customer. | 20 | All | DONE | 20 | 6 | 5 | 4 | 3 | 1 | 1 | 20
Create test case for estimating time | 5 | Netra Dahal | Done | 5 | 2 | 1 | 1 |  | 1 |  | 5
test the estimate time | 5 | Sushan tha Shrestha | Done | 5 | 2 | 1 | 1 | 1 |  |  | 5
Develop the estimate time | 5 | Biju Ale | Done | 5 | 1 | 2 | 1 | 1 |  |  | 5
Review and push | 5 | Romisha thapa | Done | 5 | 1 | 1 | 1 | 1 |  | 1 | 5
T7U2 As an admin, I want to view customer details so that I can contact the customer later. | 20 | All | DONE | 20 | 7 | 4 | 3.5 | 2.5 | 2 | 1 | 20
Create test case to view customer details | 6 | Netra Dahal | Done | 6 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 6
Implement | 5 | Sushan tha Shrestha | Done | 5 | 2 | 1 | 1 | 0.5 | 0.5 |  | 5
Create routes and views | 6 | Biju Ale | Done | 6 | 2 | 1 | 1 | 1 | 1 |  | 6
Review and push | 3 | Romisha thapa | Done | 3 | 1 | 1 | 0.5 | 0 |  | 0.5 | 3
TOTAL |  |  |  | 80 | 20 | 18 | 15 | 11 | 6 |  | 80

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.